## Iteration 3
Our plan for iteration 3 is to finish the unimplemented features of our application and build more features from the MOSCOW table if there is sufficient time left to do so, or if the client request any more extra features. * the marked text in red repesent addional features
Iteration 3
Assigned team member(s) | Task description | Planned work hours | Task start date | Deadline
Emil, Joseph | Database design | 3:00 | 25.05.2018 | 15.06.2018
Emil, Joseph | Database implementation | 3:00 | 25.05.2018 | 15.06.2018
Lyubomir | Set parameters for tweaking | 3:00 | 25.05.2018 | 15.06.2018
Marina | Documentation updates | 3:00 | 25.05.2018 | 15.06.2018
Ivelin | Final URS | 3:00 | 25.05.2018 | 15.06.2018
Lyubomir | Final Design Document | 3:00 | 25.05.2018 | 15.06.2018
Lyubomir | Final Test Report | 3:00 | 25.05.2018 | 15.06.2018
Vasil | Final Version of work division report | 3:00 | 25.05.2018 | 15.06.2018
Vasil | Process Report | 6:00 | 25.05.2018 | 15.06.2018
Ivelin | Application Advanced Testing | 3:00 | 25.05.2018 | 15.06.2018
Marina | Update GUI Design | 3:00 | 25.05.2018 | 15.06.2018
Marina | Change map pins | 3:00 | 25.05.2018 | 15.06.2018
Marina | Export data to PDF | 3:00 | 25.05.2018 | 15.06.2018
Whole team | Other possible features | 12:00 | 25.05.2018 | 15.06.2018
Note on B4: The database has been moved from iteration 2 to iteration 3, so to focus on iteration 2 requirement features. The database Entity framework research point has been cover in iteration 2.